## BeSmoke Gantt
GANTT CHART for BeSmoke | [28 empty] | https://goo.gl/PXLbMe
| PROJECT TITLE | BeFinanced | [5 empty] | COMPANY NAME | [8 empty] | BeSmoke
| PROJECT MANAGER | Jule O | [5 empty] | DATE | [8 empty] | 2017-09-01
[8 empty] | LEARNING | [14 empty] | SPRINT 1 | [9 empty] | SPRINT 2 | [9 empty] | SPRINT 3 | [9 empty] | SPRINT 4
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | SPRINT | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | HOURS |  | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Learning the Tools
1.1 | Software Tools | All | 2017-08-31 | 2017-09-21 | 21 |  | 100% | bar: WEEK 1 R to WEEK 3 R; WEEK 5 W; WEEK 7 M to WEEK 7 T; WEEK 9 M
1.1.1 | GIT | All | 2017-08-31 | 2017-09-21 | 21 |  | 100% | bar: WEEK 1 R to WEEK 3 R; WEEK 5 W; WEEK 7 M to WEEK 7 T; WEEK 9 M
1.2 | Atom | All | 2017-09-07 | 2017-09-21 | 14 |  | 90% | bar: WEEK 2 R to WEEK 3 R; WEEK 5 W; WEEK 7 M to WEEK 7 T; WEEK 9 M
1.3 | Gantt Chart | Jule O | 2017-09-21 | 2017-09-26 | 5 |  | 100% | bar: WEEK 2 R to WEEK 2 F; WEEK 3 R to WEEK 4 W; WEEK 5 W; WEEK 7 M to WEEK 7 T; WEEK 9 M
2 | Sprint 1
2.1 | Panels | Matt K | 2017-10-16 | 2017-10-18 | 2 | 2 | 100% | bar: WEEK 2 R to WEEK 2 F; WEEK 5 M to WEEK 5 W; WEEK 7 M to WEEK 7 T; WEEK 9 M
2.2 | Backline Work (Classes, Implementation) | Sanden E, Ian J, Erik B | 2017-10-16 | 2017-10-18 | 2 | 5.5 | 85% | bar: WEEK 2 R to WEEK 2 F; WEEK 5 M to WEEK 5 W; WEEK 7 M to WEEK 7 T; WEEK 9 M
2.3 | Bug Testing | Jule O | 2017-10-18 | 2017-10-18 | 0 | 1 | 50% | bar: WEEK 2 R to WEEK 2 F; WEEK 5 W; WEEK 7 M to WEEK 7 T; WEEK 9 M
2.4 | Presentation | Ian J | 2017-10-18 | 2017-10-18 | 0 | 0.5 | 100% | bar: WEEK 2 R to WEEK 2 F; WEEK 5 W; WEEK 7 M to WEEK 7 T; WEEK 9 M
3 | Sprint 2
3.1 | Password Class | Ian J | 2017-10-25 | 2017-10-25 | 0 | 1 | 100% | bar: WEEK 2 R to WEEK 2 F; WEEK 5 W; WEEK 6 W; WEEK 7 M to WEEK 7 T; WEEK 9 M
3.2 | Creating Views | Matt K | 2017-10-25 | 2017-10-30 | 5 | 2 | 75% | bar: WEEK 2 R to WEEK 2 F; WEEK 5 W; WEEK 6 W to WEEK 7 T; WEEK 9 M
3.3 | Working Controller Bugs | Erik B | 2017-10-25 | 2017-10-30 | 5 | 3 | 100% | bar: WEEK 2 R to WEEK 2 F; WEEK 5 W; WEEK 6 W to WEEK 7 T; WEEK 9 M
3.4 | Presentation/Logo | Ian J | 2017-11-01 | 2017-11-01 | 0 | 2 | 100% | bar: WEEK 2 R to WEEK 2 F; WEEK 5 W; WEEK 7 M to WEEK 7 T; WEEK 9 M
3.4.1 | Bug Testing | Sanden E | 2017-10-30 | 2017-11-01 | 1 | 2 | 100% | bar: WEEK 2 R to WEEK 2 F; WEEK 5 W; WEEK 7 M to WEEK 7 T; WEEK 9 M
3.3.1 | Chart Updates | Jule O | 2017-11-01 | 2017-11-01 | 0 | 1 | 100% | bar: WEEK 2 R to WEEK 2 F; WEEK 5 W; WEEK 7 M to WEEK 7 T; WEEK 9 M
4 | Sprint 3
4.1 | UI Design | Matt K | 2017-11-03 | 2017-11-13 | 10 |  | 50% | bar: WEEK 2 R to WEEK 2 F; WEEK 5 W; WEEK 7 M to WEEK 7 T; WEEK 8 M to WEEK 9 M
4.2 | Secure Password | Ian J | 2017-11-11 | 2017-11-13 | 2 | 3.5 | 100% | bar: WEEK 2 R to WEEK 2 F; WEEK 5 W; WEEK 7 M to WEEK 7 T; WEEK 8 F to WEEK 9 M
4.3 | User Documentation Write-up | Jule O | 2017-11-13 | 2017-11-13 | 0 |  | 0% | bar: WEEK 2 R to WEEK 2 F; WEEK 5 W; WEEK 7 M to WEEK 7 T; WEEK 9 M
4.4 | Gantt Chart Update | Jule O | 2017-11-13 | 2017-11-13 | 0 | 1.5 | 100% | bar: WEEK 2 R to WEEK 2 F; WEEK 5 W; WEEK 7 M to WEEK 7 T; WEEK 9 M
4.5 | Transaction Codes | Sanden E | 2017-11-13 | 2017-11-14 | 1 |  | 0% | bar: WEEK 2 R to WEEK 2 F; WEEK 5 W; WEEK 7 M to WEEK 7 T; WEEK 9 M to WEEK 9 T