## Sheet1
# | Task Name | Priority | Status | Notes
Sprint 1
1 | Username and Password Fields | Medium | Completed
2 | Login Button | Medium | Completed
3 | Account Classes | Medium | Completed
4 | Main View | High | Completed
5 | Logout Button | Medium | Completed
6 | Better name than "Placeholder" | Low | Completed | "BeFinanced"
7 | Listeners for buttons | High | Completed
Sprint 2
1 | Fix Persistant Data Issue | High | Completed
2 | Transaction Class | Medium | Completed
3 | Fix the repository after Ian f'd things up | High | Completed
4 | Update Controller | Medium | Completed
Sprint 3
1 | Promote Corporate Culture | HIGH | Completed, for now
2 | Merch Mockups | HIGH | Completed
3 | Logo Design | Medium | Completed
4 | Implement Passwardo | Medium | Completed
5 | Populate Transaction Tabs | Medium | Completed
6 | Add Home Button | Medium | Completed
7 | Package into jar | Low | Completed
Sprint 4
1 | Graphical Overhaul | Medium | Completed
2 | System Document | High | Completed
Sprint 5
1 | Implement Sick Fidget Toy with Sick Toggle Switches and Whatnot | HIGHEST | In Progress
2 | Reorganize File Structure | High-ish | Not Started
3 | Getting info from the AccountDetailsController into hash tables |  | In Progress
4 | Getting info from the TransactionDetailsController |  | In Progress
5 | Removing the sliders and adding those extra 3 types of withdrawals |  | In Progress
6 | Populating data from hash tables into the table view for: |  | In Progress
6a | AccountsController |  | In Progress
6b | TransactionsController |  | In Progress
7 | Adding functionality to select data on a table and then populating it in the: |  | In Progress
7a | AccountsController |  | In Progress
7b | TransactionsController |  | In Progress
8 | Make the DeleteController validate the current pass and put its good/bad result into the Model.goodPassword field |  | In Progress | "simply have a key, value pair like "Active" = true for not deleted in the "account" or "transaction" hash tables."
9 | Populate the delete methods for deleting a: |  | In Progress
9a | user |  | In Progress
9b | code |  | In Progress
9c | transaction |  | In Progress
9d | account |  | In Progress
10 | Populate the Accounts.fxml and Transactions.fxml with their controllers |  | In Progress
11 | Save data from the hash table |  | In Progress
12 | Load that data back up and populate the hash table upon launch |  | In Progress